## README
Portfolio budget tracker: budget, committed and actuals by month (sample)
All amounts in EUR, VAT included. Sample data: the projects, people and vendors are fictional. From Sideshore, makers of Ledgerman for Jira: sideshore.tech/ledgerman
Sheet | What it holds
Projects | Master list of portfolio projects, each linked to its Jira project key.
Budget_Plan | Approved budget: one row per project per calendar year, phased by month. Input.
Contracts | Signed contracts. Contract value plus its annual phasing (how much falls into each calendar year). Actuals to date and open balance are calculated.
Certificates | Acceptance certificates posted against contracts, one row per certificate. Input. Project, year and month are calculated.
Summary_Year | Pick a year (yellow cell). Per project: Budget vs Committed vs Actuals, uncommitted budget, open commitment, utilisation and % committed.
Monthly | Pick a year (yellow cell). Per project, month by month: Budget, Actuals, Variance and cumulative utilisation.
Colour legend
Blue text | Typed-in input. Edit these.
Black text | Formula. Don't overwrite.
Green text | Formula pulling from another sheet.
Yellow fill | Selector / key input (the reporting year).
Red fill | Check failed: annual phasing ≠ contract value, or actuals exceed contract value.
To add data | Add a row in Contracts or Certificates and copy the formulas down from the row above. Use the first rows of each sheet as the format example.

## Projects
Project ID | Jira key | Project name | Project manager | Status
P-01 | CRM | CRM modernisation | A. Lee | In progress
P-02 | DWH | Data warehouse | M. Novak | In progress
P-03 | MOB | Mobile banking app | K. Tamm | In progress
P-04 | ERP | ERP finance module | S. Berg | Planning
P-05 | SEC | Information security upgrade | L. Martin | In progress

## Budget_Plan
Project ID | Year | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year total
P-01 | 2025 | 72000 | 108000 | 144000 | 144000 | 162000 | 162000 | 144000 | 144000 | 162000 | 162000 | 180000 | 216000 | 1800000
P-01 | 2026 | 96000 | 144000 | 192000 | 192000 | 216000 | 216000 | 192000 | 192000 | 216000 | 216000 | 240000 | 288000 | 2400000
P-01 | 2027 | 48000 | 72000 | 96000 | 96000 | 108000 | 108000 | 96000 | 96000 | 108000 | 108000 | 120000 | 144000 | 1200000
P-02 | 2025 | 120000 | 180000 | 240000 | 240000 | 270000 | 270000 | 240000 | 240000 | 270000 | 270000 | 300000 | 360000 | 3000000
P-02 | 2026 | 144000 | 216000 | 288000 | 288000 | 324000 | 324000 | 288000 | 288000 | 324000 | 324000 | 360000 | 432000 | 3600000
P-02 | 2027 | 80000 | 120000 | 160000 | 160000 | 180000 | 180000 | 160000 | 160000 | 180000 | 180000 | 200000 | 240000 | 2000000
P-03 | 2025 | 48000 | 72000 | 96000 | 96000 | 108000 | 108000 | 96000 | 96000 | 108000 | 108000 | 120000 | 144000 | 1200000
P-03 | 2026 | 80000 | 120000 | 160000 | 160000 | 180000 | 180000 | 160000 | 160000 | 180000 | 180000 | 200000 | 240000 | 2000000
P-03 | 2027 | 60000 | 90000 | 120000 | 120000 | 135000 | 135000 | 120000 | 120000 | 135000 | 135000 | 150000 | 180000 | 1500000
P-04 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-04 | 2026 | 32000 | 48000 | 64000 | 64000 | 72000 | 72000 | 64000 | 64000 | 72000 | 72000 | 80000 | 96000 | 800000
P-04 | 2027 | 160000 | 240000 | 320000 | 320000 | 360000 | 360000 | 320000 | 320000 | 360000 | 360000 | 400000 | 480000 | 4000000
P-05 | 2025 | 36000 | 54000 | 72000 | 72000 | 81000 | 81000 | 72000 | 72000 | 81000 | 81000 | 90000 | 108000 | 900000
P-05 | 2026 | 56000 | 84000 | 112000 | 112000 | 126000 | 126000 | 112000 | 112000 | 126000 | 126000 | 140000 | 168000 | 1400000
P-05 | 2027 | 40000 | 60000 | 80000 | 80000 | 90000 | 90000 | 80000 | 80000 | 90000 | 90000 | 100000 | 120000 | 1000000

## Contracts
Contract No | Project ID | Vendor | Subject | Signed | Start | End | Contract total | Of which 2025 | Of which 2026 | Of which 2027 | Annual phasing check | Actuals to date | Open balance | % delivered
D-2025/014 | P-01 | Alpha Integration Ltd | CRM implementation, phase 1 | 2025-02-10 | 2025-03-01 | 2025-12-31 | 1560000 | 1560000 | 0 | 0 | OK | 1650000 | -90000 | 105.8%
D-2025/031 | P-01 | Alpha Integration Ltd | CRM implementation, phase 2 | 2025-12-15 | 2026-01-01 | 2027-06-30 | 3000000 | 0 | 2100000 | 900000 | OK | 1714000 | 1286000 | 57.13%
D-2025/008 | P-02 | Beta Data Services Ltd | DWH platform build | 2025-01-20 | 2025-02-01 | 2026-12-31 | 5600000 | 2600000 | 3000000 | 0 | OK | 5158000 | 442000 | 92.11%
D-2026/002 | P-02 | Gamma Licensing Ltd | DWH licences & support | 2026-01-25 | 2026-02-01 | 2027-01-31 | 610000 | 0 | 550000 | 60000 | OK | 404000 | 206000 | 66.23%
D-2025/019 | P-03 | Delta Mobile Studio | Mobile app MVP | 2025-04-05 | 2025-05-01 | 2026-03-31 | 1470000 | 1050000 | 420000 | 0 | OK | 1470000 | 0 | 100%
D-2026/011 | P-03 | Delta Mobile Studio | Mobile app release 2 | 2026-03-20 | 2026-04-01 | 2026-12-31 | 1350000 | 0 | 1350000 | 0 | OK | 765000 | 585000 | 56.67%
D-2026/020 | P-04 | Epsilon ERP Partners | ERP finance blueprint | 2026-06-01 | 2026-07-01 | 2027-12-31 | 3400000 | 0 | 400000 | 3000000 | OK | 210000 | 3190000 | 6.176%
D-2025/022 | P-05 | Zeta Security Ltd | DLP rollout | 2025-05-12 | 2025-06-01 | 2026-06-30 | 1320000 | 720000 | 600000 | 0 | OK | 1320000 | 0 | 100%
D-2026/015 | P-05 | Eta Security Reseller | SIEM licences | 2026-04-08 | 2026-05-01 | 2027-04-30 | 950000 | 0 | 650000 | 270000 | Mismatch | 278000 | 672000 | 29.26%
Total | [6 empty] | 19260000 | 5930000 | 9070000 | 4230000 |  | 12969000 | 6291000 | 67.34%

## Certificates
Contract No | Certificate No | Certificate date | Period | Comment | Amount | Project ID | Year | Month
D-2025/008 | 008-01 | 2025-02-28 | Feb 2025 | Works accepted for period | 214000 | P-02 | 2025 | 2
D-2025/008 | 008-02 | 2025-03-28 | Mar 2025 | Works accepted for period | 242000 | P-02 | 2025 | 3
D-2025/014 | 014-01 | 2025-03-28 | Mar 2025 | Works accepted for period | 148000 | P-01 | 2025 | 3
D-2025/008 | 008-03 | 2025-04-28 | Apr 2025 | Works accepted for period | 246000 | P-02 | 2025 | 4
D-2025/014 | 014-02 | 2025-04-28 | Apr 2025 | Works accepted for period | 140000 | P-01 | 2025 | 4
D-2025/008 | 008-04 | 2025-05-28 | May 2025 | Works accepted for period | 227000 | P-02 | 2025 | 5
D-2025/014 | 014-03 | 2025-05-28 | May 2025 | Works accepted for period | 163000 | P-01 | 2025 | 5
D-2025/019 | 019-01 | 2025-05-28 | May 2025 | Works accepted for period | 113000 | P-03 | 2025 | 5
D-2025/008 | 008-05 | 2025-06-28 | Jun 2025 | Works accepted for period | 240000 | P-02 | 2025 | 6
D-2025/014 | 014-04 | 2025-06-28 | Jun 2025 | Works accepted for period | 136000 | P-01 | 2025 | 6
D-2025/019 | 019-02 | 2025-06-28 | Jun 2025 | Works accepted for period | 138000 | P-03 | 2025 | 6
D-2025/022 | 022-01 | 2025-06-28 | Jun 2025 | Works accepted for period | 276000 | P-05 | 2025 | 6
D-2025/008 | 008-06 | 2025-07-28 | Jul 2025 | Works accepted for period | 205000 | P-02 | 2025 | 7
D-2025/014 | 014-05 | 2025-07-28 | Jul 2025 | Works accepted for period | 158000 | P-01 | 2025 | 7
D-2025/019 | 019-03 | 2025-07-28 | Jul 2025 | Works accepted for period | 142000 | P-03 | 2025 | 7
D-2025/008 | 008-07 | 2025-08-28 | Aug 2025 | Works accepted for period | 205000 | P-02 | 2025 | 8
D-2025/014 | 014-06 | 2025-08-28 | Aug 2025 | Works accepted for period | 150000 | P-01 | 2025 | 8
D-2025/019 | 019-04 | 2025-08-28 | Aug 2025 | Works accepted for period | 134000 | P-03 | 2025 | 8
D-2025/008 | 008-08 | 2025-09-28 | Sep 2025 | Works accepted for period | 216000 | P-02 | 2025 | 9
D-2025/014 | 014-07 | 2025-09-28 | Sep 2025 | Works accepted for period | 135000 | P-01 | 2025 | 9
D-2025/019 | 019-05 | 2025-09-28 | Sep 2025 | Works accepted for period | 146000 | P-03 | 2025 | 9
D-2025/022 | 022-02 | 2025-09-28 | Sep 2025 | Works accepted for period | 263000 | P-05 | 2025 | 9
D-2025/008 | 008-09 | 2025-10-28 | Oct 2025 | Works accepted for period | 249000 | P-02 | 2025 | 10
D-2025/014 | 014-08 | 2025-10-28 | Oct 2025 | Works accepted for period | 156000 | P-01 | 2025 | 10
D-2025/019 | 019-06 | 2025-10-28 | Oct 2025 | Works accepted for period | 124000 | P-03 | 2025 | 10
D-2025/008 | 008-10 | 2025-11-28 | Nov 2025 | Works accepted for period | 231000 | P-02 | 2025 | 11
D-2025/014 | 014-09 | 2025-11-28 | Nov 2025 | Works accepted for period | 134000 | P-01 | 2025 | 11
D-2025/019 | 019-07 | 2025-11-28 | Nov 2025 | Works accepted for period | 139000 | P-03 | 2025 | 11
D-2025/008 | 008-11 | 2025-12-28 | Dec 2025 | Works accepted for period | 325000 | P-02 | 2025 | 12
D-2025/014 | 014-10 | 2025-12-28 | Dec 2025 | Works accepted for period | 330000 | P-01 | 2025 | 12
D-2025/019 | 019-08 | 2025-12-28 | Dec 2025 | Works accepted for period | 114000 | P-03 | 2025 | 12
D-2025/022 | 022-03 | 2025-12-28 | Dec 2025 | Works accepted for period | 181000 | P-05 | 2025 | 12
D-2025/008 | 008-12 | 2026-01-28 | Jan 2026 | Works accepted for period | 256000 | P-02 | 2026 | 1
D-2025/019 | 019-09 | 2026-01-28 | Jan 2026 | Works accepted for period | 143000 | P-03 | 2026 | 1
D-2025/031 | 031-01 | 2026-01-28 | Jan 2026 | Works accepted for period | 152000 | P-01 | 2026 | 1
D-2025/008 | 008-13 | 2026-02-28 | Feb 2026 | Works accepted for period | 246000 | P-02 | 2026 | 2
D-2025/019 | 019-10 | 2026-02-28 | Feb 2026 | Works accepted for period | 138000 | P-03 | 2026 | 2
D-2025/031 | 031-02 | 2026-02-28 | Feb 2026 | Works accepted for period | 154000 | P-01 | 2026 | 2
D-2025/008 | 008-14 | 2026-03-28 | Mar 2026 | Works accepted for period | 235000 | P-02 | 2026 | 3
D-2025/019 | 019-11 | 2026-03-28 | Mar 2026 | Works accepted for period | 139000 | P-03 | 2026 | 3
D-2025/022 | 022-04 | 2026-03-28 | Mar 2026 | Works accepted for period | 290000 | P-05 | 2026 | 3
D-2025/031 | 031-03 | 2026-03-28 | Mar 2026 | Works accepted for period | 171000 | P-01 | 2026 | 3
D-2026/002 | 002-01 | 2026-03-28 | Mar 2026 | Works accepted for period | 122000 | P-02 | 2026 | 3
D-2025/008 | 008-15 | 2026-04-28 | Apr 2026 | Works accepted for period | 272000 | P-02 | 2026 | 4
D-2025/031 | 031-04 | 2026-04-28 | Apr 2026 | Works accepted for period | 192000 | P-01 | 2026 | 4
D-2025/008 | 008-16 | 2026-05-28 | May 2026 | Works accepted for period | 265000 | P-02 | 2026 | 5
D-2025/031 | 031-05 | 2026-05-28 | May 2026 | Works accepted for period | 155000 | P-01 | 2026 | 5
D-2025/008 | 008-17 | 2026-06-28 | Jun 2026 | Works accepted for period | 231000 | P-02 | 2026 | 6
D-2025/022 | 022-05 | 2026-06-28 | Jun 2026 | Works accepted for period | 310000 | P-05 | 2026 | 6
D-2025/031 | 031-06 | 2026-06-28 | Jun 2026 | Works accepted for period | 160000 | P-01 | 2026 | 6
D-2026/002 | 002-02 | 2026-06-28 | Jun 2026 | Works accepted for period | 134000 | P-02 | 2026 | 6
D-2025/008 | 008-18 | 2026-07-28 | Jul 2026 | Works accepted for period | 256000 | P-02 | 2026 | 7
D-2025/031 | 031-07 | 2026-07-28 | Jul 2026 | Works accepted for period | 182000 | P-01 | 2026 | 7
D-2025/008 | 008-19 | 2026-08-28 | Aug 2026 | Works accepted for period | 252000 | P-02 | 2026 | 8
D-2025/031 | 031-08 | 2026-08-28 | Aug 2026 | Works accepted for period | 199000 | P-01 | 2026 | 8
D-2026/011 | 011-01 | 2026-08-28 | Aug 2026 | Works accepted for period | 765000 | P-03 | 2026 | 8
D-2026/015 | 015-01 | 2026-08-28 | Aug 2026 | Works accepted for period | 278000 | P-05 | 2026 | 8
D-2025/008 | 008-20 | 2026-09-28 | Sep 2026 | Works accepted for period | 278000 | P-02 | 2026 | 9
D-2025/031 | 031-09 | 2026-09-28 | Sep 2026 | Works accepted for period | 179000 | P-01 | 2026 | 9
D-2026/002 | 002-03 | 2026-09-28 | Sep 2026 | Works accepted for period | 148000 | P-02 | 2026 | 9
D-2026/020 | 020-01 | 2026-09-28 | Sep 2026 | Works accepted for period | 210000 | P-04 | 2026 | 9
D-2025/008 | 008-21 | 2026-10-28 | Oct 2026 | Works accepted for period | 267000 | P-02 | 2026 | 10
D-2025/031 | 031-10 | 2026-10-28 | Oct 2026 | Works accepted for period | 170000 | P-01 | 2026 | 10

## Summary_Year
Portfolio budget summary for year: |  |  | 2025
EUR. Change the yellow cell to switch year.
Project ID | Project name | Annual budget | Committed for year | Actuals in year | Uncommitted budget (budget − committed) | Open commitment (committed − actuals) | Utilisation (actuals / budget) | % committed (committed / budget)
P-01 | CRM modernisation | 1800000 | 1560000 | 1650000 | 240000 | -90000 | 91.67% | 86.67%
P-02 | Data warehouse | 3000000 | 2600000 | 2600000 | 400000 | 0 | 86.67% | 86.67%
P-03 | Mobile banking app | 1200000 | 1050000 | 1050000 | 150000 | 0 | 87.5% | 87.5%
P-04 | ERP finance module | 0 | 0 | 0 | 0 | 0 | 0% | 0%
P-05 | Information security upgrade | 900000 | 720000 | 720000 | 180000 | 0 | 80% | 80%
Portfolio total |  | 6900000 | 5930000 | 6020000 | 970000 | -90000 | 87.25% | 85.94%

## Monthly
Monthly budget vs actuals for year: |  |  | 2025
EUR. Year follows Summary_Year!D1.
Project ID | Metric | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year total
P-01 | Budget | 72000 | 108000 | 144000 | 144000 | 162000 | 162000 | 144000 | 144000 | 162000 | 162000 | 180000 | 216000 | 1800000
P-01 | Actuals | 0 | 0 | 148000 | 140000 | 163000 | 136000 | 158000 | 150000 | 135000 | 156000 | 134000 | 330000 | 1650000
P-01 | Variance (actuals − budget) | -72000 | -108000 | 4000 | -4000 | 1000 | -26000 | 14000 | 6000 | -27000 | -6000 | -46000 | 114000 | -150000
P-01 | Cumulative utilisation % | 0% | 0% | 45.68% | 61.54% | 71.59% | 74.12% | 79.59% | 82.87% | 82.93% | 84.47% | 83.33% | 91.67% | 91.67%
P-02 | Budget | 120000 | 180000 | 240000 | 240000 | 270000 | 270000 | 240000 | 240000 | 270000 | 270000 | 300000 | 360000 | 3000000
P-02 | Actuals | 0 | 214000 | 242000 | 246000 | 227000 | 240000 | 205000 | 205000 | 216000 | 249000 | 231000 | 325000 | 2600000
P-02 | Variance (actuals − budget) | -120000 | 34000 | 2000 | 6000 | -43000 | -30000 | -35000 | -35000 | -54000 | -21000 | -69000 | -35000 | -400000
P-02 | Cumulative utilisation % | 0% | 71.33% | 84.44% | 90% | 88.48% | 88.56% | 88.08% | 87.72% | 86.71% | 87.35% | 86.17% | 86.67% | 86.67%
P-03 | Budget | 48000 | 72000 | 96000 | 96000 | 108000 | 108000 | 96000 | 96000 | 108000 | 108000 | 120000 | 144000 | 1200000
P-03 | Actuals | 0 | 0 | 0 | 0 | 113000 | 138000 | 142000 | 134000 | 146000 | 124000 | 139000 | 114000 | 1050000
P-03 | Variance (actuals − budget) | -48000 | -72000 | -96000 | -96000 | 5000 | 30000 | 46000 | 38000 | 38000 | 16000 | 19000 | -30000 | -150000
P-03 | Cumulative utilisation % | 0% | 0% | 0% | 0% | 26.9% | 47.54% | 62.98% | 73.19% | 81.28% | 85.15% | 88.64% | 87.5% | 87.5%
P-04 | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-04 | Actuals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-04 | Variance (actuals − budget) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-04 | Cumulative utilisation % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P-05 | Budget | 36000 | 54000 | 72000 | 72000 | 81000 | 81000 | 72000 | 72000 | 81000 | 81000 | 90000 | 108000 | 900000
P-05 | Actuals | 0 | 0 | 0 | 0 | 0 | 276000 | 0 | 0 | 263000 | 0 | 0 | 181000 | 720000
P-05 | Variance (actuals − budget) | -36000 | -54000 | -72000 | -72000 | -81000 | 195000 | -72000 | -72000 | 182000 | -81000 | -90000 | 73000 | -180000
P-05 | Cumulative utilisation % | 0% | 0% | 0% | 0% | 0% | 69.7% | 58.97% | 51.11% | 86.8% | 76.78% | 68.06% | 80% | 80%
Portfolio | Budget | 276000 | 414000 | 552000 | 552000 | 621000 | 621000 | 552000 | 552000 | 621000 | 621000 | 690000 | 828000 | 6900000
Portfolio | Actuals | 0 | 214000 | 390000 | 386000 | 503000 | 790000 | 505000 | 489000 | 760000 | 529000 | 504000 | 950000 | 6020000
Portfolio | Variance (actuals − budget) | -276000 | -200000 | -162000 | -166000 | -118000 | 169000 | -47000 | -63000 | 139000 | -92000 | -186000 | 122000 | -880000